## Revision History
Product Backlog Revision History
Version | Notes | Modified By | Date
1 | Original Version | David Gould | 2016-01-26

## Product Backlog
Product Backlog
ID | Rank | User Story | Story Points | Status | Iteration | Added By | Added On | Row Labels | Sum of Story Points
1 | 1 | As a user, I want a simple GUI | 3 | In Progress |  | Gino | 2016-01-19 | (blank) | 73
2 | 1 | As a user, I want to play music (mp3s) | 5 | Not Started |  | Gino | 2016-01-19 | Grand Total | 73
3 | 2 | As a user, I want to view my music | 3 | Not Started |  | Gino | 2016-01-19
4 | 2 | As a user, I want to import music | 8 | Not Started |  | Gino | 2016-01-20
5 | 3 | As a user, I want to shuffle music | 8 | Not Started |  | David | 2016-01-26
6 | 1 | As a user, I want to pause music | 3 | Not Started |  | David | 2016-01-26
7 | 3 | As a user, I want to organize music | 8 | Not Started |  | David | 2016-01-26
8 | 3 | As a user, I want to create playlists | 5 | Not Started |  | David | 2016-01-26
9 | 4 | As a user, I want to add music to the playing queue | 5 | Not Started |  | David | 2016-01-26
10 | 2 | As a user, I want to skip songs | 1 | Not Started |  | David | 2016-01-26
11 | 4 | As a user, I want to be able to import multiple file types (mp3, wav, etc) | 3 | Not Started |  | David | 2016-01-26
12 | 4 | As a user, I want to repeat songs | 5 | Not Started |  | Gino | 2016-01-26
13 | 5 | As a user, I want to see album artwork | 8 | Not Started |  | Gino | 2016-01-26
14 | 5 | As a user, I want an advanced GUI | 8 | Not Started |  | Gino | 2016-01-26
15 | 1 | As a user, I want to be able to control the volume | 3 | Not Started |  | Gino | 2016-01-27
16 | 4 | As a user, I want to see see song information | 3 | Not Started |  | Gino | 2016-01-27
17 | 3 | As a user, I want to scrub through songs | 5 | Not Started |  | Gino | 2016-01-27
*NOTE: To refresh chart data, right click on the chart and select "Refresh Data"