## Revision History
Sprint Backlog Revision History
Version | Notes | Modified By | Date
1 | Initial version | Team Member | 2015-03-15
1.1 | Added a new task | Different Member | 2015-03-20
1.2 | Added my work details for first scrum | Dev One | 2015-03-21
1.3 | Added my work details for first scrum | Dev Two | 2015-03-21

## Sprint Backlog
Sprint Backlog
|  |  |  | IDEAL PATH: | 44 | 38.5 | 33 | 27.5 | 22 | 16.5 | 11 | 5.5 | 0
ID | Story ID | Task Description | Assigned To | Status | Estimate | 2016-01-25 | 2016-01-26 | 2016-01-27 | 2016-01-28 | 2016-01-29 | 2016-01-30 | 2016-01-31 | 2016-02-01 | Remaining
1 | 1 | Create a basic GUI with Play/pause, next/previous, volumn slider. | Nick | Complete | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 1 | Shuffle, playlist, etc. Buttons to add | Nick | Complete | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 2 | File structure | Trevor | Not Started | 16 | 0 | [7 empty] | 16
4 | 2 | Song Object | Trevor | Not Started | 16 | 0 | [7 empty] | 16
5 | 6 | Volumn Control | David | Not Started | 4 | 0 | [7 empty] | 4
6 | 6 | Pause and Play | Gino | Not Started | 5 | 0 | [7 empty] | 5
7 |  |  |  | Not Started | [9 empty] | 0
8 |  |  |  | Not Started | [9 empty] | 0
9 |  |  |  | Not Started | [9 empty] | 0
10 |  |  |  | Not Started | [9 empty] | 0
11 |  |  |  | Not Started | [9 empty] | 0
12 |  |  |  | Not Started | [9 empty] | 0
13 |  |  |  | Not Started | [9 empty] | 0
14 |  |  |  | Not Started | [9 empty] | 0
15 |  |  |  | Not Started | [9 empty] | 0
|  |  |  | WORK REMAINING: | 44 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41
This shape represents a table slicer. Table slicers are supported in Excel 2013 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are supported in Excel 2013 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are supported in Excel 2013 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.